## SSS Main
CLIN | Task Name | Comments | Delivery Place | WAEDC | SOW Ref. | Qty | Unit Price | Total Price
1 | WP1 - Project Management
1.1 | Delivery and Acceptance of Project Implementation Plan (PIP) |  |  |  | 2.6 | 1
1.1.1 | Delivery and Acceptance of Final PIP |  | NCI Agency | 16 | 2.6 | 1
1.1.2 | Delivery and Acceptance of PIP updates until FSA |  | NCI Agency | 2 wks before each PRM | 2.6 | lot
1.2 | Support Meetings
1.2.1 | Support Kick-off Meeting (KOM) |  | NCI Agency | 2 | 3.4.7,3.5 | 1
1.2.2 | Support Project Review Meetings (PRM) |  | NCI Agency |  | 2.9 | lot
1.2.3 | Support Ad-hoc Meetings (AHM) |  | NCI Agency |  | 2.1 | lot
1.3 | Provide Reports
1.3.1 | Delivery and Acceptance of Project Highlight Reports (PHR) |  | NCI Agency |  | 2.7 | lot
1.4 | Establish and Maintain NeCT
1.4.1 | Delivery and Acceptance of NeCT Engagement Procedures |  | NCI Agency | 34 | 2.8 | lot
1.4.2 | Deploy NeCT to Mons |  | NCI Agency, Mons | 38 | 2.3.8 | lot
1.4.3 | Sustain NeCT presence in Mons |  | NCI Agency, Mons | FSA | 2.3.8, 2.3.9 | lot
1.4.4 | Augment NeCT for SRTS |  | NCI Agency, Mons | FSA | 5.5.1 | lot
1.5 | Contract REACH laptop service |  | NCI Agency | 1 | 2.4.1 | lot
WP2 - System Design
2.1 | Review System Requirements
2.1.1 | Conduct System Requirements Review (SRR) |  | NCI Agency | 10 | 3.4.1 | lot
2.1.2 | Delivery and Acceptance of SRR Report |  | NCI Agency | 10 | 3.4.1 | lot
2.2 | Conduct Configuration Capturing
2.2.1 | Perform Configuration Capturing activities |  | NCI Agency, Mons | 10 | 3.4.2 | lot
2.2.2 | Delivery and Acceptance of Configuration Capturing Report (CCR) |  | NCI Agency | 11 | 3.4.2 | lot
2.3 | Conduct Site Surveys
2.3.1 | Delivery and Acceptance of Site Survey Report (SSR) Template |  | NCI Agency | 6 | 3.4.4 | 1
2.3.2 | Conduct Site Survey Batch #1 (no. of sites as per Contractor's plan) |  | NCI Location | 10 | 3.4.4 | lot
2.3.3 | Conduct Site Survey Batch #2 (no. of sites as per Contractor's plan) |  | NCI Location | 16 | 3.4.4 | lot
2.3.4 | Conduct Site Survey Batch #3 (no. of sites as per Contractor's plan) |  | NCI Location | 22 | 3.4.4 | lot
2.3.5 | Conduct Site Survey Batch #4 (no. of sites as per Contractor's plan) |  | NCI Location | 28 | 3.4.4 | lot
2.3.6 | Delivery and Acceptance of Site Survey Reports (SSR), one per batch |  | NCI Agency | 31 | 3.4.4 | lot
2.4 | Delivery and Acceptance of System Design Specification (SDS) |  |  | 40 | 3.4.5 | lot
2.5 | Proof of Concept (PoC)
2.5.1 | Supply of PoC platform |  | NCI Agency, Mons | 12 | 3.4.6 | 1
2.5.2 | Install and configure PoC platform |  | NCI Agency, Mons | 16 | 3.4.6 | 1
2.5.3 | Execute Security Testing and Verification Plan (STVP) |  | NCI Agency, Mons | 18 34 | 4.5.1 | 1
2.5.4 | Deleted Support Purchaser's CCP Process |  | NCI Agency, Mons | 36 | 4.5.2 | 1
2.5.5 | Delivery and Acceptance of PoC Training Material |  | NCI Agency, Mons | 22 | 9.4.3,9.5 | 1
2.5.6 | Conduct PoC Training (train-the-tester) |  | NCI Agency, Mons | 22 | 9.4.3 | 1
2.6 | System Design Reviews
2.6.1 | Conduct Critical Design Review (CDR) during PRM-1 |  | NCI Agency | 12 | 3.4.7 | 1
2.6.2 | Conduct Intermediate Design Review (IDR) during PRM-2 |  | NCI Agency | 18 | 3.4.7 | 1
2.6.3 | Conduct Test Readiness Review (TRR) during PRM-3 |  | NCI Agency | 24 | 3.4.4, 3.4.6.2, 3.4.7 | 1
2.6.4 | Conduct Intermediate Design Review (IDR) during PRM-4 |  | NCI Agency | 30 | 3.4.7, 4.3.1 | 1
2.6.5 | Conduct Final Design Review (FDR) during PRM-5 |  | NCI Agency | 36 | 3.4.7 | 1
3 | WP3 - CIS Security
3.1 | Provide subsystem-specific Security Accreditation Support Packages (SASP) |  | NCI Agency | 34 | 4.3.1 | 4
3.2 | Provide global network Security Accreditation Support Package (SASP) |  | NCI Agency | 34 | 4.3.1 | 1
3.3 | Support to Purchaser's CCP Process |  |  | 36 | 4.3.1 | 1
3.3.1 | Support to Penetration testing |  | NCI Agency, Mons | 36 | 4.5.2.1 | lot
3.3.2 | Support to Vulnerability Testing |  | NCI Agency, Mons | 36 12 | 4.5.2.2 | lot
4 | WP4 - System Implementation |  |  | 12 | 4.5.2.2 | lot
4.1 | WP4.1 - Prepare System Implementation
4.1.1 | Conduct Installation Readiness Reviews (IRR-1 to IRR-5) |  | NCI Agency | PRM-5 to PRM-9 | 5.2,5.3 | 5
4.1.2 | Delivery and Acceptance of SIDP Batch #1 (as per Site Survey Batch #1) |  | NCI Agency | 16 | 5.2 | lot
4.1.3 | Delivery and Acceptance of SIDP Batch #2 (as per Site Survey Batch #2) |  | NCI Agency | 22 | 5.2 | lot
4.1.4 | Delivery and Acceptance of SIDP Batch #3 (as per Site Survey Batch #3) |  | NCI Agency | 28 | 5.2 | lot
4.1.5 | Delivery and Acceptance of SIDP Batch #4 (as per Site Survey Batch #4) |  | NCI Agency | 34 | 5.2 | lot
4.2 | WP4.2 - Implementation and Acceptance of R&TF
4.2.1 | Supply of equipment |  | NCI Agency, Mons
4.2.1.1 | NCI Reference Subsystems |  | NCI Agency, Mons | 32 34 | 5.3.1 | 1
4.2.1.2 | Software Licenses |  | NCI Agency, Mons | 32 34 | 5.3.1 | 1
4.2.1.3 | Tools, Test Equipment and Consumables |  | NCI Agency, Mons | 32 34 | 5.3.1 | 1
4.2.2 | Conduct Installation |  | NCI Agency, Mons | 34 37 | 5.3.1 | 1
4.2.3 | Delivery and Acceptance of Documentation |  | NCI Agency | 34 | 5.3.1,10 | 1
4.2.4 | Delivery and Acceptance of updated CMDB (PBL) |  | NCI Agency, Mons | 37 | 5.3.1 | 1
4.2.5 | Conduct STVP Testing |  | NCI Agency, Mons | 35 33 | 5.3.1 | 1
4.2.6 | Deleted Conduct Training |  | NCI Agency, Mons | 34 | 9.4.2 | 1
4.2.7 | Conduct System Testing |  | NCI Agency, Mons | 37 36 | 6 | 1
4.2.8 | Conduct PSA Meeting |  | NCI Agency | 39 | 8.3.3 | 1
4.2.9 | Delivery and Acceptance of PSA Report |  | NCI Agency | 39 | 8.3.2 | 1
4.3 | WP4.3 - Network Operations Centres (3 sites)
4.3.1 | Supply of NCI equipment |  | NCI NOC Locations Mons,Brunssum, Castlegate | 40 | 5.3,5.6.1 | 3
4.3.2 | Conduct Installation |  | NCI NOC Locations Mons,Brunssum, Castlegate | 41 | 5.3,5.6.1 | 3
4.3.3 | Delivery and Acceptance of Documentation |  | NCI Agency | 40 | 10 | 3
4.3.4 | Delivery and Acceptance of updated CMDB (PBL) |  | NCI NOC Locations Mons,Brunssum, Castlegate | 45 | 13.7 | 3
4.3.5 | Conduct STVP Testing |  | NCI NOC Locations Mons,Brunssum, Castlegate | 42 33 | 4.5.1 | lot
4.3.6 | Conduct Training |  | NCI NOC Locations Mons,Brunssum, Castlegate | 43 41 | 9.4.6 | lot
4.3.7 | Conduct System Testing |  | NCI NOC Locations Mons,Brunssum, Castlegate | 45 | 6 | 3
4.3.8 | Delivery and Acceptance of PSA Report |  | NCI Agency | 45 | 8.3.2 | 3
4.3.9 | Provide OpEval Support |  | NCI NOC Locations Mons,Brunssum, Castlegate | NLT T1 + 24 months | 7.1 | 3
4.3.10 | Provide Ancillary Services Infrastructure |  | NCI NOC Locations Mons,Brunssum, Castlegate | 41 | 5.3.5 | lot
4.3.11 | Provide Virtualized Services and Applications Infrastructure
4.3.11.1 | Provide physical computing, storage and networking infrastructure |  | NCI NOC DC Locations Mons, Castlegate | 41 | 5.3.6 | lot
4.3.11.2 | Provide hypervisor infrastructure |  | NCI NOC DC Locations Mons, Castlegate | 41 | 5.3.6 | lot
4.3.12 | Conduct Subscribers Migration |  | NCI NOC Locations Mons, The Hague | 46 | 7 | 2
4.4 | WP4.4 - Wave 1 Implementation and Acceptance (14 sites)
4.4.1 | Supply of NCI equipment |  | NCI Location | NLT T1 + 24 months | 5.3,5.6.2 | 14
4.4.2 | Conduct Installation |  | NCI Location | NLT T1 + 24 months | 5.3,5.6.2 | 14
4.4.3 | Delivery and Acceptance of Documentation |  | NCI Agency | 2 wks before PSA meeting | 10 | 14
4.4.4 | Delivery and Acceptance of updated CMDB (PBL) |  | NOC Locations | 2 wks before PSA meeting | 13.7 | 14
4.4.5 | Conduct STVP Testing |  | NCI Agency, Mons + NCI Location | NLT T1 + 24 months 33 | 4.5.1 | lot
4.4.6 | Deleted Conduct Training |  | NCI Agency | 34 | 9.4.5,9.6 | lot
4.4.7 | Conduct System Testing |  | NCI Location | NLT T1 + 24 months | 6 | 14
4.4.8 | Conduct Subscribers Migration |  | NCI Location | NLT T1 + 24 months | 7 | 14
4.4.9 | Delivery and Acceptance of PSA Report |  | NCI Agency | 2 wks before PSA meeting | 8.3.2 | 14
4.4.10 | Provide OpEval Support |  | NCI Location | NLT T1 + 24 months | 7.1 | 14
4.5 | WP4.5 - Wave 2 Implementation and Acceptance (10 sites)
4.5.1 | Supply of NCI equipment |  | NCI Location | NLT T1 + 24 months | 5.3,5.6.3 | 10
4.5.2 | Conduct Installation |  | NCI Location | NLT T1 + 24 months | 5.3,5.6.3 | 10
4.5.3 | Delivery and Acceptance of Documentation |  | NCI Agency | 2 wks before PSA meeting | 10 | 10
4.5.4 | Delivery and Acceptance of updated CMDB (PBL) |  | NOC Locations | 2 wks before PSA meeting | 13.7 | 10
4.5.5 | Conduct STVP Testing |  | NCI Agency, Mons | NLT T1 + 24 months 33 | 4.5.1 | lot
4.5.6 | Deleted Conduct Training |  | NCI Agency | 34 | 9.4.5,9.6 | lot
4.5.7 | Conduct System Testing |  | NCI Location | NLT T1 + 24 months | 6 | 10
4.5.8 | Conduct Subscribers Migration |  | NCI Location | NLT T1 + 24 months | 7 | 10
4.5.9 | Delivery and Acceptance of PSA Report |  | NCI Agency | 2 wks before PSA meeting | 8.3.2 | 10
4.5.10 | Provide OpEval Support |  | NCI Location | NLT T1 + 24 months | 7.1 | 10
4.6 | WP4.6 - Wave 3 Implementation and Acceptance (23 sites)
4.6.1 | Supply of NCI equipment |  | NCI Location | NLT T1 + 24 months | 5.3,5.6.4 | 23
4.6.2 | Conduct Installation |  | NCI Location | NLT T1 + 24 months | 5.3,5.6.4 | 23
4.6.3 | Delivery and Acceptance of Documentation |  | NCI Agency | 2 wks before PSA meeting | 10 | 23
4.6.4 | Delivery and Acceptance of updated CMDB (PBL) |  | NOC Locations | 2 wks before PSA meeting | 13.7 | 23
4.6.5 | Conduct STVP Testing |  | NCI Agency, Mons + NCI Location | NLT T1 + 24 months 33 | 4.5.1 | lot
4.6.6 | Deleted Conduct Training |  | NCI Location | 34 | 9.4.5,9.6 | lot
4.6.7 | Conduct System Testing |  | NCI Agency | NLT T1 + 24 months | 6 | 23
4.6.8 | Conduct Subscribers Migration |  | NCI Location | NLT T1 + 24 months | 7 | 23
4.6.9 | Delivery and Acceptance of PSA Report |  | NCI Agency | 2 wks before PSA meeting | 8.3.2 | 23
4.6.10 | Provide OpEval Support |  | NCI Location | NLT T1 + 24 months | 7.1 | 23
4.7 | WP4.7 - Wave 4 Implementation and Acceptance (23 sites)
4.7.1 | Supply of equipment |  | NCI Location | NLT T1 + 24 months | 5.3,5.6.5 | 23
4.7.2 | Conduct Installation |  | NCI Location | NLT T1 + 24 months | 5.3,5.6.5 | 23
4.7.3 | Delivery and Acceptance of Documentation |  | NCI Agency | 2 wks before PSA meeting | 10 | 23
4.7.4 | Delivery and Acceptance of updated CMDB (PBL) |  | NOC Locations | 2 wks before PSA meeting | 13.7 | 23
4.7.5 | Conduct STVP Testing |  | NCI Agency, Mons + NCI Location | NLT T1 + 24 months 33 | 4.5.1 | lot
4.7.6 | Deleted Conduct Training |  | NCI Agency | 34 | 9.4.5,9.6 | lot
4.7.7 | Conduct System Testing |  | NCI Location | NLT T1 + 24 months | 6 | 23
4.7.8 | Conduct Subscribers Migration |  | NCI Location | NLT T1 + 24 months | 7 | 23
4.7.9 | Delivery and Acceptance of PSA Report |  | NCI Agency | 2 wks before PSA meeting | 8.3.2 | 23
4.7.10 | Provide OpEval Support |  | NCI Location | NLT T1 + 24 months | 7.1 | 23
5 | WP5 - System Migration, Testing and Acceptance
5.1 | Delivery and Acceptance of Verification Cross-Reference Matrix (VCRM) |  | NCI Agency | 40 | 6.3.1 | 1
5.2 | Delivery and Acceptance of PoCT Procedures |  | NCI Agency | 22 | 6.5.2 | 1
5.3 | Conduct PoC Testing |  | NCI Agency, Mons | 33 | 6.5
5.4 | Delivery and Acceptance of PoCT Report |  | NCI Agency | 34 | 6.5.2 | 1
5.5 | Delivery and Acceptance of General PSAT Procedures |  | NCI Agency | 40 | 6.6.2 | 1
5.6 | Conduct PSA Meetings (5) |  | NCI Agency | NLT 2 wks following PSA notification | 8.3.3 | 5
5.7 | Delivery and Acceptance of Migration Support Package |  | NCI Agency | 40 | 7.6 | 1
5.8 | Delivery and Acceptance of Migration Reports |  | NCI Agency | 2 wks before PSA Meeting | 7.7 | lot
5.9 | Delivery and Acceptance of Baseline Service Catalogue |  | NCI Agency | 2 wks prior to FSA meeting | 7.8 | 1
5.10 | Delivery and Acceptance of Baseline Service Level Agreement |  | NCI Agency | 2 wks prior to FSA meeting | 7.9 | 1
5.11 | Delivery and Acceptance of FSAT Procedures |  | NCI Agency | 2 wks before PSA meeting 4 | 6.7.2 | 1
5.12 | Conduct FSAT |  | NCI Locations |  | 6.7
5.13 | Delivery and Acceptance of FSAT Report |  | NCI Agency | 2 wks after FSAT | 6.7.3 | 1
5.14 | Delivery and Acceptance of FSA Report |  | NCI Agency | 2 wks prior to FSA meeting | 8.4.2 | 1
5.15 | Conduct FSA Meeting |  | NCI Agency | NLT T1 + 24 months
6 | WP6 - Training
6.1 | Delivery and Acceptance of TNA Report |  | NCI Agency | 30 | 9.3 | 1
6.2 | Delivery and Acceptance of CBT material |  | NCI Agency | 34 | 9.4.5 | lot
6.3 | Delivery and Acceptance of Level 2 Support training courses |  | NCI Agency | 34 | 9.4.6,9.5 | lot
6.4 | Delivery and Acceptance of Level 3 Support training courses |  | NCI Agency | 34 | 9.4.6,9.5 | lot
6.5 | Delivery and Acceptance of Train-the-PoC-Tester training material |  | NCI Agency | 22 | 9.4.3,9.5 | lot
6.6 | Conduct Train-the-PoC-Tester training course |  | NCI Agency, Mons | 22 | 9.4.3 | lot
6.7 | Delivery and Acceptance of Train-the-PSA-Tester training material |  | NCI Agency | 34 | 9.4.6,9.5 | lot
6.8 | Conduct Train-the-PSA-Tester training course |  | NCI Agency | 34 | 9.4.4 | lot
6.9 | Delivery and Acceptance of Reference and Testing System training material |  | NCI Agency | 34 | 9.4.2,9.5 | lot
6.10 | Conduct Reference and Testing System training course |  | NCI Agency | 36 34 | 9.4.2 | lot
6.11 | Delivery and Acceptance of Introduction course training material |  | NCI Agency | 4 | 9.4.1 | lot
6.12 | Conduct Introduction course |  | NCI Agency | 4 | 9.4.1 | 1
6.13 | Delivery and Acceptance of Training Evaluation Reports |  | NCI Agency | 2 wks after each training | 9.6 | lot
7 | WP7 - Integrated Logistics Support, Quality Assurance and Configuration Management
7.1 | WP7.1 - Support Planning
7.1.1 | Delivery and Acceptance of the LSAP and ISSP |  | NCI Agency | 34 | 11.2 | 1
7.2 | WP7.2 - Logistics Support Analysis, including RAMT
7.2.1 | Perform RAMT modelling and prediction |  | NCI Agency | 10 | 11.4.2,11.4.3 | 1
7.2.2 | Perform FMECA |  | NCI Agency | 10 | 11.4.4 | 1
7.2.3 | Perform Task Analysis |  | NCI Agency | 28 | 11.4.5 | 1
7.2.4 | Perform Maintainability Demonstration |  | NCI Agency | FSA | 11.4.7 | 1
7.2.5 | Delivery and Acceptance of Support Case | includes equipment data sheets, RBDs, RAMT predictions, FMECA results, Task Analysis results, Maintenance Demonstration report and RSPL | NCI Agency | 40 | 11.4.1 | 1
7.3 | WP7.3 - Supply Support
7.3.1 | Delivery and Acceptance of System Inventory |  | NCI Agency | prior to 1st PCA | 11.5.1 | 1
7.3.2 | Conduct Initial Provisioning Meeting | includes provision of Minutes of Meeting | NCI Agency | prior to 1st PSA | 11.5.4 | 1
7.3.3 | Delivery and Acceptance of SWDL |  | NCI Agency | with FSA report | 11.5.5 | 1
7.4 | WP7.4 - PHS&T
7.4.1 | Shipments, Delivery and Acceptance of equipment | includes Notices of Shipment, Packing Lists and Customs 302 Forms | NCI Location | prior to each shipment | 11.6 | lot
7.4.2 | Delivery and Acceptance of Transportation Reports |  | NCI Location | after each shipment | 11.6 | lot
7.5 | WP7.5 - Warranty
7.5.1 | Warranty and warranty management | warranty integrated into first year of CLS | NCI Location | FSA | 11.7,11.8 | lot
7.6 | WP7.6 - Contractor Logistics Support (CLS), year 1
7.6.1 | Provide Obsolescence support |  | NCI Location | FSA | 11.8.1,11.8.2 | lot
7.6.2 | OEM vendor 24/7/4 support contracts | in accordance with the Purchaser approved allocation of support stategies | NCI Location | FSA | 11.8.1,11.8.2 | lot
7.6.3 | OEM vendor 8/5/NBD support contracts | in accordance with the Purchaser approved allocation of support stategies | NCI Location | FSA | 11.8.1,11.8.2 | lot
7.6.4 | Delivery and Aceptance of On-site spares | in accordance with the Purchaser approved allocation of support stategies | NCI Location | FSA | 11.8.1,11.8.2 | lot
7.6.5 | Level 3 and 4 software support, including technical assistance and service desk support |  | NCI Location | FSA | 11.8 | lot
7.6.6 | Software licenses and software license renewals |  | NCI Location | FSA | 11.822 | lot
7.6.7 | Annual Refreshment Training Programme (ARTP), including CBT refresh |  | NCI Agency | FSA | 11.8.3 | lot
7.6.8 | Documentation support |  | NCI Agency | FSA | 11.8.4 | lot
7.7 | WP7.7 - Quality Assurance (QA)
7.7.1 | Delivery and Acceptance of QAP |  | NCI Agency | 34 | 12.3 | 1
7.7.2 | Delivery and Acceptance of QAP updates until FSA |  | NCI Agency
7.7.3 | Delivery and Acceptance of QA log |  | NCI Agency | 2 wks before each PRM | 12.5 | 1
7.8 | WP7.8 - Configuration Management (CM)
7.8.1 | Delivery and Acceptance of initial CMDB (FBL) |  | NCI Agency | 10 | 13.7 | 1
7.8.2 | Delivery and Acceptance of CMDB update (ABL) |  | NCI Agency | 40 | 13.7 | 1
7.8.3 | Delivery and Acceptance of CMDB update (OBL) |  | NCI Agency | with FSA report | 13.7 | lot
7.8.4 | Conduct Functional Configuration Audit (FCA) |  | NCI Agency | 4 wks before PSA mtg 1 | 13.6 | 1
7.8.5 | Delivery and Acceptance of FCA Report |  | NCI Agency | 2 wks before PSA mtg 1 | 13.6 | 1
7.8.6 | Delivery and Acceptance of the CMP |  | NCI Agency | 34 | 13.2 | 1
7.8.7 | Delivery and Acceptance of CMP updates until FSA |  | NCI Agency | 2 weeks before PRM | 13.2 | 1
7.8.8 | Delivery and Acceptance of the CI-tree |  | NCI Agency | 34 | 13.3
7.8.9 | Delivery and Acceptance of CSA Reports |  | NCI Agency | with FSA report | 13.5 | lot
7.8.10 | Conduct Physical Configuration Audits (PCAs, one per site) |  | NCI Location | NLT PSAT | 13.6 | lot
7.8.11 | Delivery and Acceptance of PCA Reports |  | NCI Agency | 2 wks before PSA | 13.6 | lot
GRAND TOTAL FIRM FIXED PRICE FOR BASE CONTRACT (CLINS 1 through 7)
8 | WP8 - Evaluated Options
8.1 | WP8.1 - Optional Contractor Logistics Support (CLS), year 2 | same as CLIN 7.6
8.1.1 | Obsolescence support |  | NCI Location | Y2 | 11.8.1,11.8.2 | lot
8.1.2 | OEM vendor 24/7/4 support contracts |  | NCI Location | Y2 | 11.8.1,11.8.2 | lot
8.1.3 | OEM vendor 8/5/NBD support contracts |  | NCI Location | Y2 | 11.8.1,11.8.2 | lot
8.1.4 | On-site spares |  | NCI Location | Y2 | 11.8.1,11.8.2 | lot
8.1.5 | Level 3 and 4 software support, including technical assistance and service desk support |  | NCI Location | Y2 | 11.8 | lot
8.1.6 | Software licenses and software license renewals |  | NCI Location | Y2 | 11.822 | lot
8.1.7 | Annual Refreshment Training Programme (ARTP), including CBT refresh |  | NCI Agency | Y2 | 11.8.3 | lot
8.1.8 | Documentation support |  | NCI Agency | Y2 | 11.8.4 | lot
8.2 | WP8.2 - Optional Contractor Logistics Support (CLS), year 3 | same as CLIN 7.6
8.2.1 | Provide Obsolescence support |  | NCI Location | Y3 | 11.8.1,11.8.2 | lot
8.2.2 | OEM vendor 24/7/4 support contracts |  | NCI Location | Y3 | 11.8.1,11.8.2 | lot
8.2.3 | OEM vendor 8/5/NBD support contracts |  | NCI Location | Y3 | 11.8.1,11.8.2 | lot
8.2.4 | Delivery and Aceptance of On-site spares |  | NCI Location | Y3 | 11.8.1,11.8.2 | lot
8.2.5 | Level 3 and 4 software support, including technical assistance and service desk support |  | NCI Location | Y3 | 11.8 | lot
8.2.6 | Software licenses and software license renewals |  | NCI Location | Y3 | 11.822 | lot
8.2.7 | Annual Refreshment Training Programme (ARTP), including CBT refresh |  | NCI Agency | Y3 | 11.8.3 | lot
8.2.8 | Documentation support |  | NCI Agency | Y3 | 11.8.4 | lot
8.3 | WP8.3 - Optional Contractor Logistics Support (CLS), year 4 | same as CLIN 7.6
8.3.1 | Provide Obsolescence support |  | NCI Location | Y4 | 11.8.1,11.8.2 | lot
8.3.2 | OEM vendor 24/7/4 support contracts |  | NCI Location | Y4 | 11.8.1,11.8.2 | lot
8.3.3 | OEM vendor 8/5/NBD support contracts |  | NCI Location | Y4 | 11.8.1,11.8.2 | lot
8.3.4 | Delivery and Aceptance of On-site spares |  | NCI Location | Y4 | 11.8.1,11.8.2 | lot
8.3.5 | Level 3 and 4 software support, including technical assistance and service desk support |  | NCI Location | Y4 | 11.8 | lot
8.3.6 | Software licenses and software license renewals |  | NCI Location | Y4 | 11.822 | lot
8.3.7 | Annual Refreshment Training Programme (ARTP), including CBT refresh |  | NCI Agency | Y4 | 11.8.3 | lot
8.3.8 | Documentation support |  | NCI Agency | Y4 | 11.8.4 | lot
8.4 | WP8.4 - Optional Contractor Logistics Support (CLS), year 5 | same as CLIN 7.6
8.4.1 | Provide Obsolescence support |  | NCI Location | Y5 | 11.8.1,11.8.2 | lot
8.4.2 | OEM vendor 24/7/4 support contracts |  | NCI Location | Y5 | 11.8.1,11.8.2 | lot
8.4.3 | OEM vendor 8/5/NBD support contracts |  | NCI Location | Y5 | 11.8.1,11.8.2 | lot
8.4.4 | Delivery and Aceptance of On-site spares |  | NCI Location | Y5 | 11.8.1,11.8.2 | lot
8.4.5 | Level 3 and 4 software support, including technical assistance and service desk support |  | NCI Location | Y5 | 11.8 | lot
8.4.6 | Software licenses and software license renewals |  | NCI Location | Y5 | 11.822 | lot
8.4.7 | Annual Refreshment Training Programme (ARTP), including CBT refresh |  | NCI Agency | Y5 | 11.8.3 | lot
8.4.8 | Documentation support |  | NCI Agency | Y5 | 11.8.4 | lot
8.5 | WP8.5 - Optional Locations (8 sites)
8.5.1 | Supply and delivery of equipment |  | NCI Location | as required | 5.3,5.6.2 | up to 8
8.5.2 | Conduct Installation |  | NCI Location | as required | 5.3,5.6.2 | up to 8
8.5.3 | Delivery and Acceptance of Documentation |  | NCI Agency | as required | 10 | up to 8
8.5.4 | Delivery and Acceptance of updated CMDB with CI's implemented |  | NOC Locations | as required | 13.7 | up to 8
8.5.5 | Conduct STVP Testing |  | NCI Location Agency, Mons | as required | 4.5.1 | lot
8.5.6 | Deleted Conduct Training |  | NCI Agency | as required | 9.4.5,9.6 | lot
8.5.7 | Conduct System Testing |  | NCI Location | as required | 6 | up to 8
8.5.8 | Conduct Subscribers Migration |  | NCI Location | as required | 7 | up to 8
8.5.9 | Delivery and Acceptance of PSA Report |  | NCI Agency | as required | 8.3.2 | up to 8
8.5.10 | Provide OpEval Support |  | NCI Agency, Mons | as required | 7.1 | up to 8
8.5.11 | Conduct Site Survey and provide Site Survey Report |  | NCI Location | as required | 3.3.2, 3.4.4 | up to 8
8.6 | WP8.6 - Optional NU LAN Switches in MMA subsystem (25 sites)
8.6.1 | NU LAN Switches in NOC Sites (1 site) |  | NCI Location | With implementation of Site | 5.3.2.3 | 1
8.6.2 | NU LAN Switches in Wave 1 locations (5 sites) |  | NCI Location | With implementation of Site | 5.3.2.3 | 5
8.6.3 | NU LAN Switches in Wave 2 locations (6 sites) |  | NCI Location | With implementation of Site | 5.3.2.3 | 6
8.6.4 | NU LAN Switches in Wave 3 locations (11 sites) |  | NCI Location | With implementation of Site | 5.3.2.3 | 11
8.6.5 | NU LAN Switches in Wave 4 locations (2 sites) |  | NCI Location | With implementation of Site | 5.3.2.3 | 2
8.7 | WP8.7 - Supply, Delivery and Installation of NATO-NDN Gateways (31 sites)
8.7.1 | NATO-NDN Gateway in NOC Sites (3 sites) |  | NCI Location | With implementation of Site | 5.3.2.3,Appendix 6 | 3
8.7.2 | NATO-NDN Gateway in Wave 1 locations (7 sites) |  | NCI Location | With implementation of Site | 5.3.2.3,Appendix 6 | 7
8.7.3 | NATO-NDN Gateway in Wave 2 locations (3 sites) |  | NCI Location | With implementation of Site | 5.3.2.3,Appendix 6 | 3
8.7.4 | NATO-NDN Gateway in Wave 3 locations (2 sites) |  | NCI Location | With implementation of Site | 5.3.2.3,Appendix 6 | 2
8.7.5 | NATO-NDN Gateway in Wave 4 locations (16 sites) |  | NCI Location | With implementation of Site | 5.3.2.3,Appendix 6 | 16
9 | WP9 - Non-evaluated Options
9.1 | WP9.1 - NCI Expansion Options
9.1.1 | Network growth
9.1.1.1 | Additional NCI Node
9.1.1.1.1 | Conduct Site Survey and provide Site Survey Report |  | NCI Location | as required | 3.4.4 | 1
9.1.1.1.2 | Provide SISRS and STVP |  | NCI Agency | as required | 4.3.1 | 1
9.1.1.1.3 | Additional Support to Purchaser's CCP Process |  | NCI Agency, Mons | as required | 4.5.2 | 1
9.1.1.1.4 | Delivery and Acceptance of SIDP |  | NCI Agency | as required | 5.2 | 1
9.1.1.1.5 | Supply and delivery of NCI equipment |  | NCI Location | as required | 5.3,5.6.2 | 1
9.1.1.1.6 | Conduct Installation |  | NCI Location | as required | 5.3,5.6.2 | 1
9.1.1.1.7 | Delivery and Acceptance of Documentation |  | NCI Agency | as required | 10 | 1
9.1.1.1.8 | Delivery and Acceptance of updated CMDB (PBL) with CI's implemented |  | NOC Locations | as required | 13.7 | 1
9.1.1.1.9 | Conduct STVP Testing |  | NCI Agency, Mons | as required | 4.5.1 | 1
9.1.1.1.10 | Deleted Conduct Training |  | NCI Agency | as required | 9.4.5,9.6 | 1
9.1.1.1.11 | Conduct System Testing |  | NCI Location | as required | 6 | 1
9.1.1.1.12 | Conduct Subscribers Migration |  | NCI Location | as required | 7 | 1
9.1.1.1.13 | Delivery and Acceptance of PSA Report |  | NCI Agency | as required | 8.3.2 | 1
9.1.1.1.14 | Provide OpEval Support |  | NCI Agency, Mons | as required | 7.1 | 1
9.1.1.2 | Additional 5G NCI Node
9.1.1.2.1 | Conduct Site Survey and provide Site Survey Report |  | NCI Location | as required | 3.4.4 | 1
9.1.1.2.2 | Provide SISRS and STVP |  | NCI Agency | as required | 4.3.1 | 1
9.1.1.2.3 | Additional Support to Purchaser's CCP Process |  | NCI Agency, Mons | as required | 4.5.2 | 1
9.1.1.2.4 | Delivery and Acceptance of SIDP |  | NCI Agency | as required | 5.2 | 1
9.1.1.2.5 | Supply and delivery of NCI equipment |  | NCI Location | as required | 5.3,5.6.2 | 1
9.1.1.2.6 | Conduct Installation |  | NCI Location | as required | 5.3,5.6.2 | 1
9.1.1.2.7 | Delivery and Acceptance of Documentation |  | NCI Agency | as required | 10 | 1
9.1.1.2.8 | Delivery and Acceptance of updated CMDB (PBL) with CI's implemented |  | NOC Locations | as required | 13.7 | 1
9.1.1.2.9 | Conduct STVP Testing |  | NCI Agency, Mons | as required | 4.5.1 | 1
9.1.1.2.10 | Deleted Conduct Training |  | NCI Agency | as required | 9.4.5,9.6 | 1
9.1.1.2.11 | Conduct System Testing |  | NCI Location | as required | 6 | 1
9.1.1.2.12 | Conduct Subscribers Migration |  | NCI Location | as required | 7 | 1
9.1.1.2.13 | Delivery and Acceptance of PSA Report |  | NCI Agency | as required | 8.3.2 | 1
9.1.1.2.14 | Provide OpEval Support |  | NCI Agency, Mons | as required | 7.1 | 1
9.1.1.3 | 1G NCI Node |  | NCI Location | as required | 3.3.2 | 1
9.1.1.4 | 100M Node |  | NCI Location | as required | 3.3.2 | 1
9.1.1.5 | Pico NED
9.1.1.5.1 | Pico-NEDs in E3 configuration |  | NCI Location | as required | Appendix 7 | 1
9.1.1.5.2 | Pico-NEDs in E1 E3 and serial configuration |  | NCI Location | as required | Appendix 7 | 1
9.1.2 | Single Node growth
9.1.2.1 | Additional SECRET CC to CCA
9.1.2.1.1 | Additional SECRET CC to an NCI 40G Node |  | NCI Location | as required | 3.3.2.2.1 | 1
9.1.2.1.2 | Additional SECRET CC to an NCI 5G Node |  | NCI Location | as required | 3.3.2.2.1 | 1
9.1.2.1.3 | Additional SECRET to an NCI 100M Node |  | NCI Location | as required | 3.3.2.2.1 | 1
9.1.2.1.4 | Additional SECRET CC to an NCI 1G Node |  | NCI Location | as required | 3.3.2.2.1 | 1
9.1.2.2 | Additional RESTRICTED CC to CCA
9.1.2.2.1 | Additional RESTRICTED CC to an NCI 40G Node |  | NCI Location | as required | 3.3.2.2.2 | 1
9.1.2.2.2 | Additional RESTRICTED CC to an NCI 5G Node |  | NCI Location | as required | 3.3.2.2.2 | 1
9.1.2.2.3 | Additional RESTRICTED CC to an NCI 100M Node |  | NCI Location | as required | 3.3.2.2.2 | 1
9.1.2.2.4 | Additional RESTRICTED CC to an NCI 1G Node |  | NCI Location | as required | 3.3.2.2.2 | 1
9.1.2.3 | Additional UNCLASSFIED CC to CCA
9.1.2.3.1 | Additional UNCLASSFIED CC to an NCI 40G Node |  | NCI Location | as required | 3.3.2.2.3 | 1
9.1.2.3.2 | Additional UNCLASSFIED CC to an NCI 5G Node |  | NCI Location | as required | 3.3.2.2.3 | 1
9.1.2.3.3 | Additional UNCLASSFIED CC to an NCI 100M Node |  | NCI Location | as required | 3.3.2.2.3 | 1
9.1.2.3.4 | Additional UNCLASSFIED CC to an NCI 1G Node |  | NCI Location | as required | 3.3.2.2.3 | 1
9.1.2.4 | Additional VoIP user appliances
9.1.2.4.1 | NU Voice End-user appliances
9.1.2.4.1.1 | Location with 50 appliances ( incl. switches licences cabling and ancillaries) |  | NCI Location | With implementation of Site | 5.3.2.3 | 1
9.1.2.4.1.2 | Location with 100 appliances ( incl. switches licences cabling and ancillaries) |  | NCI Location | With implementation of Site | 5.3.2.3 | 1
9.1.2.4.1.3 | Location with 500 appliances ( incl. switches licences cabling and ancillaries) |  | NCI Location | With implementation of Site | 5.3.2.3 | 1
9.1.2.4.1.4 | Location with 1000 appliances ( incl. switches licences cabling and ancillaries) |  | NCI Location | With implementation of Site | 5.3.2.3 | 1
9.1.2.4.2 | Additional number of user appliances
9.1.2.4.2.1 | Batch of 10 Additional phones ( incl. switches licences cabling and ancillaries) |  | NCI Location | as required | 3.3.2.2.4 | 1
9.1.2.4.2.2 | Batch of 50 Additional phones ( incl. switches licences cabling and ancillaries) |  | NCI Location | as required | 3.3.2.2.4 | 1
9.1.2.4.2.3 | Batch of 100 Additional phones ( incl. switches licences cabling and ancillaries) |  | NCI Location | as required | 3.3.2.2.4 | 1
9.1.2.5 | Additional Interfaces
9.1.2.5.1 | Additional communications interfaces to a PCA subsystem instance |  | NCI Location | as required | 3.3.2.3 | 1
9.1.2.5.2 | Additional communications interfaces to a CCA subsystem instance |  | NCI Location | as required | 3.3.2.3 | 1
9.1.2.5.3 | Additional communications interfaces to MMA subsystem instance |  | NCI Location | as required | 3.3.2.3 | 1
9.1.3 | Performance Growth
9.1.3.1 | Upgrade a NCI 5G Node to a NCI 40G Node |  | NCI Location | as required | 3.3.2.3 | 1
9.1.3.2 | Upgrade a NCI 5G Node to 20G |  | NCI Location | as required | 3.3.2.3 | 1
9.1.3.3 | Upgrade an NCI 20G node to a NCI 40G Node |  | NCI Location | as required | 3.3.2.3 | 1
9.2 | WP9.2 - Horizontal and Vertical Cabling, NU LAN switches, VoIP appliances (10 sites)
9.2.1 | Horizontal and Vertical Cabling, NU LAN switches, VoIP appliances in NOC sites (2 sites) |  | NCI Location | With implementation of Site | 5.3.2.3 | 2
9.2.2 | Horizontal and Vertical Cabling, NU LAN switches, VoIP appliances in Wave 1 sites (2 sites) |  | NCI Location | With implementation of Site | 5.3.2.3 | 2
9.2.3 | Horizontal and Vertical Cabling, NU LAN switches, VoIP appliances in Wave 2 sites (3 sites) |  | NCI Location | With implementation of Site | 5.3.2.3 | 3
9.2.4 | Horizontal and Vertical Cabling, NU LAN switches, VoIP appliances in Wave 3 sites (1 site) |  | NCI Location | With implementation of Site | 5.3.2.3 | 1
9.2.5 | Horizontal and Vertical Cabling, NU LAN switches, VoIP appliances in Wave 4 sites (2 sites) |  | NCI Location | With implementation of Site | 5.3.2.3 | 2
9.3 | WP9.3 - Circuit Emulation Subsystem (CES)
9.3.1 | Supply and Delivery of Alcatel 7705 |  | NCI Location | as required | Appendix 8 | 1
9.3.2 | Installation |  | NCI Location | as required | Appendix 8 | 1
9.3.3 | Testing |  | NCI Location | as required | Appendix 8 | 1
9.3.4 | Documentation |  | NCI Agency | as required | Appendix 8 | 1
9.4 | WP9.4 - NU LAN Switches in MMA subsystem (25 sites)
9.4.1 | NU LAN Switches in NOC Sites (1 site) |  | NCI Location | With implementation of Site | 5.3.2.3 | 1
9.4.2 | NU LAN Switches in Wave 1 locations (5 sites) |  | NCI Location | With implementation of Site | 5.3.2.3 | 5
9.4.3 | NU LAN Switches in Wave 2 locations (6 sites) |  | NCI Location | With implementation of Site | 5.3.2.3 | 6
9.4.4 | NU LAN Switches in Wave 3 locations (11 sites) |  | NCI Location | With implementation of Site | 5.3.2.3 | 11
9.4.5 | NU LAN Switches in Wave 4 locations (2 sites) |  | NCI Location | With implementation of Site | 5.3.2.3 | 2

## NOC (3 sites)
CLIN | NOC Sites (3 sites) | NOC Mons (BEL) | NOC Supporting site Lago Patria (ITA) | NOC The Hague (NLD)
1 | Supply of NCI equipment
1.1 | PCA subsystem
1.2 | CCA subsystem (NS domain)
1.3 | CCA subsystem (NU/NR domain)
1.4 | MMA subsystem (NU domain)
1.5 | Management subsystem (NS domain)
1.6 | Management subsystem (NU/NR domain)
1.7 | NU VoIP Appliances
1.8 | Software Licenses
1.9 | Tools Test Equipment and Consumables
1.10 | Transport of PFE
2 | Conduct Installation
2.1 | Installation of NCI equipment
2.2 | Installation of PFE
3 | Delivery and Acceptance of Documentation
3.1 | OEM COTS documentation
3.2 | Operations Manuals
3.3 | Maintenance Manuals
3.4 | As-built Drawings
3.5 | NCI Documentation Store (doc. wikis)
3.6 | CIS Security Documentation
3.7 | ILS Documentation
3.8 | Training documentation
4 | Delivery and Acceptance of updated CMDB (PBL)
5 | Conduct STVP Testing
6 | Conduct Training
7 | Conduct System Testing
7.1 | Generate Service Requests
7.2 | Delivery and Acceptance of PSAT Procedures
7.3 | Conduct PSAT
7.4 | Delivery and Acceptance of PSAT Report
8 | Conduct Subscribers Migration
9 | Delivery and Acceptance of PSA Report
10 | Provide OpEval Support
EVALUATED OPTIONS
11 | NU LAN Switches in MMA Subsystem
11.1 | Supply and Delivery of NU LAN Switches
11.2 | Installation
11.3 | Testing and Acceptance
12 | NATO-NDN Gateway in MMA Subsystem
12.1 | Supply and Delivery of NATO-NDN Gateway
12.2 | Installation
12.3 | Testing and Acceptance
NON-EVALUATED OPTIONS
13 | Horizontal Cabling, NU LAN switches, VoIP appliances
13.1 | Supply and Delivery of NU LAN Switches
13.2 | Supply and Delivery of Horizontal Cabling
13.3 | Supply and Delivery of NU VoIP Appliances
13.4 | Installation of Horizontal Cabling
13.5 | Installation of NU LAN Switches and VoIP app.
13.6 | Testing and Acceptance
13.7 | Additional Batch of 10 Telecom Outlets
13.8 | Additional Batch of 10 NU VoIP appliances
14 | NU LAN Switches in MMA Subsystem
14.1 | Supply and Delivery of NU LAN Switches
14.2 | Installation
14.3 | Testing and Acceptance

## Wave 1 (14 sites)
CLIN | WAVE 1 (14 sites) | Brussels (NATO HQ IMS/IS, NSO, NSTO-OCS, NCIA) - BEL | Kester (SGT F01) - BEL | Karup (NATO PoP) - DNK | Lyon (NATO PoP) - FRA | Northwood (MARCOM) - GBR | Athens (NATO PoP) - GRC | Castlegate (ACO Bunker) - DEU | Lughezzano (SGT F14) - ITA | Sigonella (AGS) - ITA | Brunssum - NLD | Izmir Disko Hit (Bunker + NCI Agency PoP) - TUR | Izmir Gen. Vecihi (LANDCOM, 3 NSB DCM-F) - TUR | Oglananasi (SGT F13) - TUR | Norfolk (ACT HQ) - USA
1 | Supply of NCI equipment
1.1 | PCA subsystem
1.2 | CCA subsystem (NS domain)
1.3 | CCA subsystem (NU/NR domain)
1.4 | MMA subsystem (NU domain)
1.5 | Management subsystem (NS domain)
1.6 | Management subsystem (NU/NR domain)
1.7 | NU VoIP Appliances
1.8 | Software Licenses
1.9 | Tools Test Equipment and Consumables
1.10 | Transport of PFE
2 | Conduct Installation
2.1 | Installation of NCI equipment
2.2 | Installation of PFE
3 | Delivery and Acceptance of Documentation
3.1 | OEM COTS documentation
3.2 | Operations Manuals
3.3 | Maintenance Manuals
3.4 | As-built Drawings
3.5 | NCI Documentation Store (doc. wikis)
3.6 | CIS Security Documentation
3.7 | ILS Documentation
3.8 | Training documentation
4 | Delivery and Acceptance of updated CMDB (PBL)
5 | Conduct STVP Testing
6 | Conduct Training
7 | Conduct System Testing
7.1 | Generate Service Requests
7.2 | Delivery and Acceptance of PSAT Procedures
7.3 | Conduct PSAT
7.4 | Delivery and Acceptance of PSAT Report
8 | Conduct Subscribers Migration
9 | Delivery and Acceptance of PSA Report
10 | Provide OpEval Support
EVALUATED OPTIONS
11 | NU LAN Switches in MMA Subsystem
11.1 | Supply and Delivery of NU LAN Switches
11.2 | Installation
11.3 | Testing and Acceptance
12 | NATO-NDN Gateway in MMA Subsystem
12.1 | Supply and Delivery of NATO-NDN Gateway
12.2 | Installation
12.3 | Testing and Acceptance
NON-EVALUATED OPTIONS
13 | Horizontal Cabling, NU LAN switches, VoIP appliances
13.1 | Supply and Delivery of NU LAN Switches
13.2 | Supply and Delivery of Horizontal Cabling
13.3 | Supply and Delivery of NU VoIP Appliances
13.4 | Installation of Horizontal Cabling
13.5 | Installation of NU LAN Switches (either PFE or Contractor supplied) and VoIP app.
13.6 | Testing and Acceptance
13.7 | Additional Batch of 10 Telecom Outlets
13.8 | Additional Batch of 10 NU VoIP appliances
13.9 | Supply and Delivery of Vertical Cabling
13.10 | Installation of Vertical Cabling
14 | NU LAN Switches in MMA Subsystem (5 sites)
14.1 | Supply and Delivery of NU LAN Switches
14.2 | Installation
14.3 | Testing and Acceptance

## Wave 2 (10 sites)
CLIN | WAVE 2 (10 sites) | Lipnik nad Becvou (3 NSB DCM-B) - CZE | Ramstein (HQ AIRCOM) - DEU | Uedem (CAOC-U) - DEU | Torrejon (CAOC-T) - ESP | Poggio Renatico (DCAOC) - ITA | Capellen (NSPA) - LUX | Stavanger, Jåttå (JWC) - NOR | Bydgoszcz (JFTC, 3 NSB HQ, M&S Coy) - POL | Monsanto (JALLC) - PRT | Oeiras (NATO CIS School) - PRT
1 | Supply of NCI equipment
1.1 | PCA subsystem
1.2 | CCA subsystem (NS domain)
1.3 | CCA subsystem (NU/NR domain)
1.4 | MMA subsystem (NU domain)
1.5 | Management subsystem (NS domain)
1.6 | Management subsystem (NU/NR domain)
1.7 | NU VoIP Appliances
1.8 | Software Licenses
1.9 | Tools Test Equipment and Consumables
1.10 | Transport of PFE
2 | Conduct Installation
2.1 | Installation of NCI equipment
2.2 | Installation of PFE
3 | Delivery and Acceptance of Documentation
3.1 | OEM COTS documentation
3.2 | Operations Manuals
3.3 | Maintenance Manuals
3.4 | As-built Drawings
3.5 | NCI Documentation Store (doc. wikis)
3.6 | CIS Security Documentation
3.7 | ILS Documentation
3.8 | Training documentation
4 | Delivery and Acceptance of updated CMDB (PBL)
5 | Conduct STVP Testing
6 | Conduct Training
7 | Conduct System Testing
7.1 | Generate Service Requests
7.2 | Delivery and Acceptance of PSAT Procedures
7.3 | Conduct PSAT
7.4 | Delivery and Acceptance of PSAT Report
8 | Conduct Subscribers Migration
9 | Delivery and Acceptance of PSA Report
10 | Provide OpEval Support
EVALUATED OPTIONS
11 | NU LAN Switches in MMA Subsystem
11.1 | Supply and Delivery of NU LAN Switches
11.2 | Installation
11.3 | Testing and Acceptance
12 | NATO-NDN Gateway in MMA Subsystem
12.1 | Supply and Delivery of NATO-NDN Gateway
12.2 | Installation
12.3 | Testing and Acceptance
NON-EVALUATED OPTIONS
13 | Horizontal Cabling, NU LAN switches, VoIP appliances
13.1 | Supply and Delivery of NU LAN Switches
13.2 | Supply and Delivery of Horizontal Cabling
13.3 | Supply and Delivery of NU VoIP Appliances
13.4 | Installation of Horizontal Cabling
13.5 | Installation of NU LAN Switches (either PFE or Contractor supplied) and VoIP app.
13.6 | Testing and Acceptance
13.7 | Additional Batch of 10 Telecom Outlets
13.8 | Additional Batch of 10 NU VoIP appliances
13.9 | Supply and Delivery of Vertical Cabling
13.10 | Installation of Vertical Cabling
14 | NU LAN Switches in MMA Subsystem (6 sites)
14.1 | Supply and Delivery of NU LAN Switches
14.2 | Installation
14.3 | Testing and Acceptance

## Wave 3 (23 sites)
CLIN | WAVE 3 (23 sites) | Gorna Malina (2 NSB DCM-F) - BGR | Elmpt (1 NSB DCM-D) - DEU | Geilenkirchen (NAEW E-3A Command) - DEU | Oberammergau (NATO School) - DEU | Wesel (1NSB, M&S Coy, DCM-A, DCM-B, DCM-C) - DEU | Haderslev (DCM-B, DCM-C) - DNK | Maison Lafitte (NATO PoP) - FRA | Paris (NSPA (CEPMA)) - FRA | Paris (NSTU (CSO/RTA)) - FRA | Aktion (NAEW FOW) - GRC | Pleso (1 NSB DCM F) - HRV | Szekesfehervar (3 NSB DCM-E) - HUN | Grazzanise (2 NSB HQ, M&S Coy, 2 NSB DCM-A, DCM-B, DCM-C, DCM-D) - ITA | La Spezia (NSTO-CMRE) - ITA | Rome (NADEFCOL) - ITA | Taranto (NSPA) - ITA | Trapani (NAEW FOB) - ITA | Vilnius (3NSB, DCM-D) - LTU | Vilnius (NATO PoP) - LTU | Oerland (NAEW FOB) - NOR | Bucharest (2 NSB, DCM-E) - ROU | Ruzomberok (3 NSB DCM-C) - SVK | Konya (NAEW FOW) - TUR
1 | Supply of NCI equipment
1.1 | PCA subsystem
1.2 | CCA subsystem (NS domain)
1.3 | CCA subsystem (NU/NR domain)
1.4 | MMA subsystem (NU domain)
1.5 | Management subsystem (NS domain)
1.6 | Management subsystem (NU/NR domain)
1.7 | NU VoIP Appliances
1.8 | Software Licenses
1.9 | Tools Test Equipment and Consumables
1.10 | Transport of PFE
2 | Conduct Installation
2.1 | Installation of NCI equipment
2.2 | Installation of PFE
3 | Delivery and Acceptance of Documentation
3.1 | OEM COTS documentation
3.2 | Operations Manuals
3.3 | Maintenance Manuals
3.4 | As-built Drawings
3.5 | NCI Documentation Store (doc. wikis)
3.6 | CIS Security Documentation
3.7 | ILS Documentation
3.8 | Training documentation
4 | Delivery and Acceptance of updated CMDB (PBL)
5 | Conduct STVP Testing
6 | Conduct Training
7 | Conduct System Testing
7.1 | Generate Service Requests
7.2 | Delivery and Acceptance of PSAT Procedures
7.3 | Conduct PSAT
7.4 | Delivery and Acceptance of PSAT Report
8 | Conduct Subscribers Migration
9 | Delivery and Acceptance of PSA Report
10 | Provide OpEval Support
EVALUATED OPTIONS
11 | NU LAN Switches in MMA Subsystem
11.1 | Supply and Delivery of NU LAN Switches
11.2 | Installation
11.3 | Testing and Acceptance
12 | NATO-NDN Gateway in MMA Subsystem
12.1 | Supply and Delivery of NATO-NDN Gateway
12.2 | Installation
12.3 | Testing and Acceptance
NON-EVALUATED OPTIONS
13 | Horizontal Cabling, NU LAN switches, VoIP appliances
13.1 | Supply and Delivery of NU LAN Switches
13.2 | Supply and Delivery of Horizontal Cabling
13.3 | Supply and Delivery of NU VoIP Appliances
13.4 | Installation of Horizontal Cabling
13.5 | Installation of NU LAN Switches (either PFE or Contractor supplied) and VoIP app.
13.6 | Testing and Acceptance
13.7 | Additional Batch of 10 Telecom Outlets
13.8 | Additional Batch of 10 NU VoIP appliances
13.9 | Supply and Delivery of Vertical Cabling
13.10 | Installation of Vertical Cabling
14 | NU LAN Switches in MMA Subsystem (12 sites)
14.1 | Supply and Delivery of NU LAN Switches
14.2 | Installation
15 | NU LAN Switches in MMA Subsystem (6 sites)

## Wave 4 (23 sites)
CLIN | WAVE 4 (23 sites) | Tirana (NATO PoP) - ALB | Brussels (NPLT EU) - BEL | Mons (SACEUR Residence) - BEL | Sofia (NATO PoP) - BGR | Butmir (NATO HQ Sarajevo) - BIH | Ottawa (NATO PoP) - CAN | Prague (NATO PoP) - CZE | Tallin (NATO PoP) - EST | Atalanti (SGT F11) - GRC | Thessaloniki (KFOR CMZ) - GRC | Zagreb (NATO PoP) - HRV | Budapest (NATO PoP) - HUN | Papa (NSPA) - HUN | Keflavik (NATO PoP) - ISL | Pristina (KFOR HQ) - KFOR | Senningen (NATO PoP) - LUX | Riga (NATO PoP) - LVA | Warsaw (NATO PoP) - POL | Bucharest (NATO Pop) - ROU | Bratislava (NATO PoP) - SVK | Ljubliana (NATO PoP) - SVN | Ankara (NATO PoP) - TUR | Washington (NATO PoP) - USA
1 | Supply of NCI equipment
1.1 | PCA subsystem
1.2 | CCA subsystem (NS domain)
1.3 | CCA subsystem (NU/NR domain)
1.4 | MMA subsystem (NU domain)
1.5 | Management subsystem (NS domain)
1.6 | Management subsystem (NU/NR domain)
1.7 | NU VoIP Appliances
1.8 | Software Licenses
1.9 | Tools Test Equipment and Consumables
1.10 | Transport of PFE
2 | Conduct Installation
2.1 | Installation of NCI equipment
2.2 | Installation of PFE
3 | Delivery and Acceptance of Documentation
3.1 | OEM COTS documentation
3.2 | Operations Manuals
3.3 | Maintenance Manuals
3.4 | As-built Drawings
3.5 | NCI Documentation Store (doc. wikis)
3.6 | CIS Security Documentation
3.7 | ILS Documentation
3.8 | Training documentation
4 | Delivery and Acceptance of updated CMDB (PBL)
5 | Conduct STVP Testing
6 | Conduct Training
7 | Conduct System Testing
7.1 | Generate Service Requests
7.2 | Delivery and Acceptance of PSAT Procedures
7.3 | Conduct PSAT
7.4 | Delivery and Acceptance of PSAT Report
8 | Conduct Subscribers Migration
9 | Delivery and Acceptance of PSA Report
10 | Provide OpEval Support
EVALUATED OPTIONS
11 | NU LAN Switches in MMA Subsystem
11.1 | Supply and Delivery of NU LAN Switches
11.2 | Installation
11.3 | Testing and Acceptance
12 | NATO-NDN Gateway in MMA Subsystem
12.1 | Supply and Delivery of NATO-NDN Gateway
12.2 | Installation
12.3 | Testing and Acceptance
NON-EVALUATED OPTIONS
13 | Horizontal Cabling, NU LAN switches, VoIP appliances
13.1 | Supply and Delivery of NU LAN Switches
13.2 | Supply and Delivery of Horizontal Cabling
13.3 | Supply and Delivery of NU VoIP Appliances
13.4 | Installation of Horizontal Cabling
13.5 | Installation of NU LAN Switches (either PFE or Contractor supplied) and VoIP app.
13.6 | Testing and Acceptance
13.7 | Additional Batch of 10 Telecom Outlets
13.8 | Additional Batch of 10 NU VoIP appliances
13.9 | Supply and Delivery of Vertical Cabling
13.10 | Installation of Vertical Cabling
14 | NU LAN Switches in MMA Subsystem (2 sites)
14.1 | Supply and Delivery of NU LAN Switches
14.2 | Installation
15 | NU LAN Switches in MMA Subsystem (6 sites)

## Optional Wave (8 sites)
CLIN | Optional Locations (8 sites) | Bad Begzabern (SGT F20) - DEU | Berlin (NATO PoP) - DEU | Euskirchen (SGT F02) - DEU | Betera (NRDC ESP) - ESP | Oakhanger (SGT F04) - GBR | Civitaveccchia (SGT F07) - ITA | Eggemoen (SGT F05) - NOR | Costa de Caparica (SGT F12) - PRT
1 | Supply and delivery of NCI equipment
1.1 | PCA subsystem
1.2 | CCA subsystem (NS domain)
1.3 | CCA subsystem (NU/NR domain)
1.4 | MMA subsystem (NU domain)
1.5 | Management subsystem (NS domain)
1.6 | Management subsystem (NU/NR domain)
1.7 | NU VoIP Appliances
1.8 | Software Licenses
1.9 | Tools Test Equipment and Consumables
1.10 | Transport of PFE
2 | Conduct Installation
2.1 | Installation of NCI equipment
2.2 | Installation of PFE
3 | Delivery and Acceptance of Documentation
3.1 | OEM COTS documentation
3.2 | Operations Manuals
3.3 | Maintenance Manuals
3.4 | As-built Drawings
3.5 | NCI Documentation Store (doc. wikis)
3.6 | CIS Security Documentation
3.7 | ILS Documentation
3.8 | Training documentation
4 | Delivery and Acceptance of updated CMDB (PBL)
5 | Conduct STVP Testing
6 | Conduct Training
7 | Conduct System Testing
7.1 | Generate Service Requests
7.2 | Delivery and Acceptance of PSAT Procedures
7.3 | Conduct PSAT
7.4 | Delivery and Acceptance of PSAT Report
8 | Conduct Subscribers Migration
9 | Delivery and Acceptance of PSA Report
10 | Provide OpEval Support